## Product backlog
Product backlog ID | Feature | Owner | Priority | Effort (in hours) | Status | Definition of done | Notes
1 | As a staff member I need to login and be presented with the options that suit me most | James | Critical | 4.5 | Done | Staff member can view the staff member menu along with the staff options | Wording adjusted to align more to users needs previous was: As a staff member I need to be able to log into the system and be taken to a staff menu
2 | As a technician I need to login and be presented with the options that suit me most | Lars | Critical | 4 | Done | Technician can view the technician menu along with the technician options | Wording adjusted to align more to users needs, previous was: As a technician I need to be able to log into the system and be taken to a technician menu
3 | As a staff member I need to be able to create a ticket with varying severity levels | Miriam | Critical | 3 | Done | Staff member can access, fill in and create a ticket with severity options. submitted ticket is opened and delivered to the service desk
4 | As a technician I need to be able to view tickets available | Lars | Critical | 2 | Done | Technician can view tickets - open and see details
5 | As a new user I need to be able to create an account | James | Critical | 3.5 | Done | User can create a new user account and login with the new credentials
6 | As a technician, I want to be assigned tickets commensurate to my helpdesk level (eg level 1) so that I don't receive tickets that I am unable to resolve. | Lars | High | 4.5 | Done | Tickets get assigned to the technician of the appropriate level
7 | As a manager I want to make sure my technicians aren't being overloaded with tickets while others have nothing to do so I need to make sure tickets are spread out evenly across technicians or if everyone has the same amount of work, given out randomly so no one is targeted. | James | High | 10 | Done | Tickets get assigned to the technician with the least tickets assigned else randomly
8 | As a technician I need to be able to change the priority of tickets if I deem them to be better solved by a higher or lower level technician. | Miriam | High | 6 | Done | Option in the technician view of tickets to change the severity level
9 | As a technician I need to be able to close tickets when they have been resolved so ticket holders know it is fixed, or if unresolved so they may escalate with the appropriate party. | John | High | 4 | Done | Option in the technician view of tickets to change ticket status
10 | As a manager I want to be able to view the results of previous tickets created and have them stored after they have been closed for 24 hours. I don't want anyone to be able to alter them after that time to maintain the integrity of our records. | John | Medium | 4.5 | Done | System will archive closed tickets after 24 hours, upon which they will not be able to be edited
11 | As a technician I need to be able to reopen a closed ticket that hasn't been archived in case of new information or if a resolution has been found. | James | Medium | 2 | Done | Closed tickets can be changed back to open within the 24 hour period of being closed, not possible with archived tickets
12 | As a staff member I need to be able to see the status of the tickets I have created so that I know if a resolution has been found or if it has been unresolved then I can escalate it with someone else. | Lars | High | 4 | Done | Staff members can view their open tickets, status but not be able to change anything
13 | As a user if I have forgotten my password, I need to be able to reset it to regain access to the system. | Miriam | Low | 4.5 | Done | Users can change their password by selecting a "forgot password" prompt and new password with override the old password
14 | As a user I need to be able to log into the system and authenticate my log in so that I can access the system | John | Critical | 8 | Done | Users are created with a username/password combination, and the system will not permit unauthenticated access
15 | As a technician, I need to be able to produce a report for a specified period of time with a history of tickets along with specific details pertaining to each ticket. This will allow me to understand the effectiveness of the service desk | Miriam | High | 16.5 | Done | Report within a specified given time frame shows details regarding tickets submitted and which of them were resolved and which remain outstanding
16 | Create a Quick Reference Guide with instructions of how to use the product | John | Critical | 7 | Done | Provides sufficient instructions for an IT staff member to copy, compile and run the Cinco Java application within their mandated platform. | Wording adjusted to meet feedback and align more with the scenario, previous was: As a marker of this assignment, I need to be able to run and test this code

## Sprint 1 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | 23 | 20 | 16 | 13 | 0 | 0 | 0
In progress | 3 | 6 | 8 | 6 | 11 | 5 | 0
Done | 0 | 0 | 2 | 5 | 8 | 6 | 5
Ideal | 26 | 21.6667 | 17.3333 | 13 | 8.6667 | 4.3333 | 0
In progress | 1 | 4 | 3 | 2 | 6 | 1 | 0
Testing | 2 | 2 | 5 | 4 | 5 | 4 | 0

## Sprint 1 backlog
Product backlog ID | Feature | Sprint backlog ID | Task | Assigned to | Effort (in hours) | Status | [6 empty] | Notes
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | As a staff member I need to be able to log into the system and be taken to a staff menu | 1.1 | Creation of a staff object class | James | 1 | To do | To do | To do | To do | In progress | Done |  | Staff is sorted catagorized as employee, nothing yet to separate staff and technicians
1 |  | 1.2 | Staff can enter in their unique log in details | James | 1 | To do | To do | To do | To do | In progress | Done
1 |  | 1.3 | System checks and authenticates user id and password | James | 1 | To do | To do | To do | To do | In progress | Done
1 |  | 1.3 | Staff gets taken to the staff menu | James | 1 | To do | To do | To do | To do | In progress | Done
2 | As a technician I need to be able to log into the system and be taken to a technician menu | 2.1 | Creation of a technician class | Lars | 1 | In progress | Testing | Done
2 |  | 2.2 | Technician can enter in their unique log in details | Lars | 1 | To do | In progress | To do | Done
2 |  | 2.3 | System checks and authenticates user id and password | Lars | 0.5 | To do | To do | To do | Done
2 |  | 2.4 | Technician gets taken to the Technician menu | Lars | 1.5 | To do | To do | To do | Done
3 | As a staff member I need to be able to create a ticket with varying severity levels | 3.1 | Creation of a ticket object class | John | 1 | To do | To do | Done
3 |  | 3.2 | A ticket fill out form, including user name, issue, description, severity level | Miriam | 2 | To do | To do | In progress | In progress | Testing | Done
4 | As a technician I need to be able to view tickets available | 4.1 | through the technician menu a technician can view open tickets and all details | Lars | 2 | To do | To do | To do | To do | Done
5 | As a new user I need to be able to create an account | 5.1 | on log in page a new user option is displayed | James | 0.5 | To do | To do | To do | To do | Done |  |  | If the password is the same as a previously created user account it will throw an error.
5 |  | 5.2 | system asks for user name, password and if they are staff or technician | James | 1 | To do | To do | To do | To do | Done
5 |  | 5.3 | A new staff member gets added with user name and password | John | 0,5 | To do | To do | To do | To do | Done
5 |  | 5.4 | A new technician gets added with user name and password | John | 0.5 | To do | To do | To do | To do | Done
5 |  | 5.5 | Takes user back to log in page with their details now in the system | James | 0.5 | To do | To do | To do | To do | In progress | Done
6 | tickets can be assigned based on their severity level |  | To be completed in a future sprint
7 | service desk assigns tickets to technicians with least tickets assigned to them |  | To be completed in a future sprint
8 | Technicians can change the ticket severity levels |  | To be completed in a future sprint
9 | Tickets can be set by technicians to "closed & resolved" or "closed & unresolved" |  | To be completed in a future sprint
10 | Closed tickets get saved/archived after 24 hours after being closed |  | To be completed in a future sprint
11 | Closed tickets can be re-opened by technicians (within that 24 hour period) |  | To be completed in a future sprint
12 | Staff members can view their tickets and their status but not reopen them if closed/archived |  | To be completed in a future sprint
13 | As a user if I have forgotten my password, I need to be able to reset it | 13.1 | Forgot password option on log in page | Miriam | 1 | To do | To do | In progress | Done
13 |  | 13.2 | System asks for user name | Miram | 0.5 | To do | In progress | Testing | Done
13 |  | 13.3 | System authenticates username | John | 1 | To do | To do | Testing | Testing | Testing | Testing | Done
13 |  | 13.4 | System replaces password with a new one | John | 1 | To do | To do | Testing | Testing | Testing | Testing | Done
14 | As a user I need to be able to log into the system and authenticate my log in | 14.1 | Create a log in menu | John | 1 | Testing | Testing | Testing | Testing | Testing | Testing | Done
14 |  | 14.2 | authenticate login | John | 3 | Testing | In progress | Testing | Testing | Testing | Testing | Done
14 |  | 14.3 | Passwords check for minimum length of 20 | James | 1 | To do | To do | To do | To do | Done
14 |  | 14.4 | Passwords check for uppercase and lowercase | James | 1 | To do | To do | To do | To do | Done
14 |  | 14.5 | Passwords check for letters and numbers | James | 1 | To do | To do | To do | To do | Done
16 | As a marker of this assignment, I need to be able to run and test this code | 16.1 | Write text file to explain how to launch and run the code by the end of this sprint | John | 4 | To do | In progress | In progress | In progress | In progress | In progress | Done | Was blocked by ICT and uncertainties regarding deployment environment

## Sprint 1 burndown
| Effort Estimate total | over 7 days
| 29.5 | 4.2143
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| Effort Remaining | 25.2857 | 21.0714 | 16.8571 | 12.6429 | 8.4286 | 4.2143 | 0
Features | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Totals
#1 | 4 |  |  |  |  | 4 |  |  | 4
#2 | 4 | 1 | 1 |  | 2 |  |  |  | 4
#3 | 3.5 |  |  | 2 | 1 | 0.5 |  |  | 3.5
#4 | 2 |  |  |  |  | 2 |  |  | 2
#5 | 4 |  |  |  |  | 4 |  |  | 4
#13 | 4 |  | 0.5 | 2 | 1 |  |  | 0.5 | 4
#14 | 6 | 4 |  |  |  | 2 |  |  | 6
#16 | 2 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 2
Totals | 29.5 | 5 | 1.75 | 4.25 | 4.25 | 12.75 | 0.5 | 1 | 29.5
| Start (Day 0) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Completed Tasks | 0 | 0 | 0 | 2 | 5 | 8 | 6 | 5
Sum Completed | 0 | 0 | 0 | 2 | 7 | 15 | 21 | 26
Remaining Effort | 29.5 | 24.5 | 22.75 | 18.5 | 14.25 | 1.5 | 1 | 0
Ideal Burndown |  | 25.2857 | 21.0714 | 16.8571 | 12.6429 | 8.4286 | 4.2143 | 0
Remaining Tasks | 26 | 26 | 26 | 24 | 19 | 11 | 5 | 0

## Sprint 2 backlog
Product backlog ID | Feature | Sprint backlog ID | Task | Assigned to | Effort (in hours) | Status | [6 empty] | Notes
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
6 | As a technician, I want to be assigned tickets commensurate to my helpdesk level (eg level 1) so that I don't receive tickets that I am unable to resolve. | 6.1 | Have ticket class hold severity | Lars | 0.5 | Done
6 |  | 6.2 | Have low and medium severity tickets be assigned to level 1 technicians | Lars | 2 |  | Testing | Done
6 |  | 6.3 | Have high severity tickets assigned to level 2 technicians | Lars | 2 |  | Testing | Done
7 | As a manager I want to make sure my technicians aren't being overloaded with tickets while others have nothing to do so I need to make sure tickets are spread out evenly across technicians or if everyone has the same amount of work, given out randomly so no one is targeted. | 7.1 | Create a method to randomly assign tickets | James | 6.5 | In progress | Testing | Done
7 |  | 7.2 | Create a method to read how many tickets technicians currently have | James | 1.5 |  | In progress | Done
7 |  | 7.3 | Adjust random method to prioritize those with less tickets. | James | 2 | In progress | Testing | Done
8 | As a technician I need to be able to change the severity of tickets if I deem them to be better solved by a higher or lower level technician. | 8.1 | Create a method to allow technicians to change severity of the tickets they have. | Miriam | 3.5 | In progress | In progress | Testing | Done
8 |  | 8.2 | Have ticket assigned through the same method as created in P7 | Miriam | 0.5 | To do | To do | In progress | Testing | Done
8 |  | 8.3 | Create menu option in Technicians menu to adjust severity | Miriam | 1.5 | In progress | In progress | In progress | Done
8 |  | 8.4 | Test to see that ticket is assigned correctly | Miriam | 0.5 | To do | To do | In progress | Testing | Done
9 | As a technician I need to be able to close tickets when they have been resolved so ticket holders know it is fixed, or if unresolved so they may escalate with the appropriate party. | 9.1 | Have ticket class hold status variable (closed (resolved/unresolved)/ open) | John | 0.5 |  | In progress | Testing | Testing | Done
9 |  | 9.2 | Create method to allow technicians to change ticket status from open to closed, assigning either resolved or unresolved | John | 1.5 |  |  | In progress | Testing | Done
9 |  | 9.3 | Have system remove ticket out of technicians list of tickets | John | 2 |  |  | In progress | In progress | Done
13 | As a user I need to be able to log into the system and authenticate my log in | 13.1 | BUGFIX: Username needs validation before password can be entered. | James | 1 |  |  |  |  | To do | Done
1 | As a staff member I need to be able to log into the system and be taken to a staff menu | 1.1 | SpecChange: Password needs to be minimum of 8 characters not 20. Add requirments at the start of the password request. | James | 0.5 |  |  |  |  | To do | Done
26

## Sprint 2 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | 2 | 2 | 0 | 0 | 2 | 0 | 0
In progress | 4 | 8 | 7 | 5 | 0 | 0 | 0
Done | 1 | 0 | 5 | 2 | 5 | 2 | 0
Ideal | 7 | 5.8333 | 4.6667 | 3.5 | 2.3333 | 1.1667 | 0
In progress | 4 | 4 | 5 | 1 | 0 | 0 | 0
Testing | 0 | 4 | 2 | 4 | 0 | 0 | 0

## Sprint 2 burndown
| Effort Estimate total | over 7 days
| 26 | 3.7143
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| Effort Remaining | 22.2857 | 18.5714 | 14.8571 | 11.1429 | 7.4286 | 3.7143 | -4.4409e-15
Features | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Totals
1 | 1 | [5 empty] | 1 |  | 1
6 | 4.5 | 2 |  | 2.5 |  |  |  |  | 4.5
7 | 10 | 4 | 4 | 2 |  |  |  |  | 10
8 | 6 | 1 |  | 3 | 2 |  |  |  | 6
9 | 4 |  | 1 | 1.5 | 1 | 0.5 |  |  | 4
13 | 0.5 | [5 empty] | 0.5 |  | 0.5
0
Totals | 26 | 7 | 5 | 9 | 3 | 0.5 | 1.5 | 0 | 26
| Start (Day 0) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Completed Tasks |  | 1 | 0 | 5 | 2 | 5 | 2 | 0
Sum Completed | 0 | 1 | 1 | 6 | 8 | 13 | 15 | 15
Remaining Effort | 26 | 19 | 14 | 5 | 2 | 1.5 | 0 | 0
Ideal Burndown |  | 22.2857 | 18.5714 | 14.8571 | 11.1429 | 7.4286 | 3.7143 | -4.4409e-15
Remaining Tasks | 15 | 14 | 14 | 9 | 7 | 2 | 0 | 0

## Sprint 3 backlog
Product backlog ID | Feature | Sprint backlog ID | Task | Assigned to | Effort (in hours) | Status | [6 empty] | Notes
[6 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
5 | As a new user I need to be able to create an account | 5.6 | Ensure phone numbers are properly validated upon account creation | James | 1 |  |  |  |  | To do | To do | Done
10 | As a manager I want to be able to view the results of previous tickets created and have them stored after they have been closed for 24 hours. I don't want anyone to be able to alter them after that time to maintain the integrity of our records. | 10.1 | Add ability for techs to close tickets (either resolved, or unresolved) | John | 0.5 | To do | In progress | Testing | Done
10 |  | 10.2 | Create logic to automatically archive closed tickets after 24 hours | John | 0.5 | To do | In progress | Testing | Done
10 |  | 10.3 | Add ability for tech to view their assigned closed and archived tickets | John | 1 | To do | In progress | Testing | Testing | Done
10 |  | 10.4 | Add ability for techs to see other closed and archived tickets that are assigned to another tech | John | 2 | To do | In progress | In progress | In progress | Testing | Done
10 |  | 10.5 | Identify that a closed ticket is archived to the end-user | John | 0.5 |  |  |  | To do | In progress | Testing | Done
11 | As a technician I need to be able to reopen a closed ticket that hasn't been archived in case of new information or if a resolution has been found. | 11.1 | Add ability to reopen closed ticket | James | 1 | To do | To do | Testing | Testing | Done
11 |  | 11.2 | Allow technician to choose new status of ticket | James | 0.5 | To do | To do | Testing | Testing | Done
11 |  | 11.3 | Prevent status editing of archived ticket | James | 0.5 | To do | To do | Testing | Testing | Done
12 | As a staff member I need to be able to see the status of the tickets I have created so that I know if a resolution has been found or if it has been unresolved then I can escalate it with someone else. | 12.1 | Allow staff member to view status of their open tickets | Lars | 2 | To do | To do | Testing | Done
12 |  | 12.2 | Create menu option for staff member to see the open tickets they created | Lars | 1 | To do | To do | Testing | Done
12 |  | 12.3 | Create method to allow staff member to see status of their open tickets | Lars | 1 | To do | To do | Testing | Done
14 | As a user I need to be able to log into the system and authenticate my log in so that I can access the system | 13.5 | Validate user and password separately | John | 0.5 |  |  |  | To do | In progress | Done
14 |  | 13.6 | Ensure application does not crash when a blank password is entered when attempting to reset a password | John | 0.5 |  |  |  |  | To do | In progress | Done
15 | As a technician, I need to be able to produce a report for a specified period of time with a history of tickets along with specific details pertaining to each ticket. This will allow me to understand the effectiveness of the service desk | 15.1 | Create method to show a report of the tickets that were created within a specified time frame. Resolved tickets should display which member submitted it and when and who attended to it along with the length of time until it was resolved. Outstanding tickets within the time frame show who submitted it and when, along with the tickets severity | Miriam | 10 | In progress | In progress | In progress | In progress | Testing | Done
15 |  | 15.2 | Create menu option for user to produce report | Miriam | 1 | In progress | In progress | In progress | Testing | Testing | Done
15 |  | 15.3 | Create method to allow user to generate report within certain time frame | Miriam | 2 | In progress | In progress | In progress | In progress | Testing | Done
15 |  | 15.4 | Allow user to view number of resolved and outstanding tickets along with necessary detail for each status type | Miriam | 3.5 | To do | To do | In progress | In progress | Testing | Done
15 |  | 15.5 | Format date in short-form for better clarity | John | 0.5 |  |  |  |  | To do | In progress | Done
15 |  | 15.6 | Add ability for technician to specify exact date-ranges for report | John | 3 |  |  |  |  | To do | In progress | Done
16 | Create a Quick Reference Guide with instructions of how to use the product | 16.2 | README file does not work. Fix to allow compilation without editing directories | John | 3 |  |  |  | To do | In progress | Done |  | Had to work within the restrictions imposed on us by target platform

## Sprint 3 burndown
| Effort Estimate total | over 7 days
| 35.5 | 5.0714
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| Effort Remaining | 30.4286 | 25.3571 | 20.2857 | 15.2143 | 10.1429 | 5.0714 | 7.1054e-15
Features | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Totals
5 | 1 | [6 empty] | 1 | 1
10 | 4.5 |  | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 4.5
11 | 2 |  |  |  | 2 |  |  |  | 2
12 | 4 |  |  | 2 | 2 |  |  |  | 4
14 | 1 |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
15 | 20 | 6 | 4 |  | 4 | 4 |  | 2 | 20
16 | 3 | [5 empty] | 1 | 2 | 3
Totals | 35.5 | 6 | 5 | 3 | 9.25 | 5.25 | 1.5 | 5.5 | 35.5
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Completed Tasks | 0 | 0 | 0 | 0 | 5 | 4 | 7 | 5
Sum Completed | 0 | 0 | 0 | 0 | 5 | 9 | 16 | 21
Remaining Effort | 35.5 | 29.5 | 24.5 | 21.5 | 12.25 | 7 | 5.5 | 0
Ideal Burndown | 35.5 | 30.4286 | 25.3571 | 20.2857 | 15.2143 | 10.1429 | 5.0714 | 7.1054e-15
Remaining Tasks | 21 | 21 | 21 | 21 | 16 | 12 | 5 | 0

## Sprint 3 stats - DO NOT CHANGE (hidden)
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
To do | 11 | 7 | 0 | 3 | 3 | 0 | 0
In progress | 3 | 7 | 14 | 9 | 8 | 4 | 0
Done | 0 | 0 | 0 | 5 | 4 | 7 | 4
Ideal | 14 | 11.6667 | 9.3333 | 7 | 4.6667 | 2.3333 | 0
In progress | 3 | 7 | 5 | 4 | 3 | 3 | 0
Testing | 0 | 0 | 9 | 5 | 5 | 1 | 0

## References - DO NOT CHANGE (hidden)
Critical | To do
High | In progress
Medium | Testing
Low | Done